## Sheet1
S.No | Month | Epic id | Name of SME / Resource Person | Trade | Video Topic | Production Stage |  |  |  | Post Production Stage |  |  |  | Output
[6 empty] | Start date | End date | Cameraman | Shooting Status | Video Editor | Start date | End date | Editing Status | Video Topic | Duration | Video Link
1 | June | EPIC-2026-PMeVidya 04 | Shri. Maria Soosai | Fitter |  | 15.08.2026 |  | Parasuraman | Completed | Hassan & Antony | 17.08.2026 |  | On Process
2 | July | EPIC-2026-PMeVidya 03 | Shri. V. Babu | COPA | COPA - Javascript: The Language of the Web | 28.07.2026 | 28.07.2026 | Parasuraman | Completed | Hassan | 29.07.2026 | 30.07.2026 | Completed | COPA - Javascript: The Language of the Web | 1:48 | https://drive.google.com/file/d/1Dt0uoxK7s2pEwJw-l1FgbFoXvArVBWk3/view?usp=sharing
|  |  |  | POT | Communication for Online Training | 28.07.2026 | 28.07.2026 | Parasuraman | Completed | Hassan | 29.07.2026 | 30.07.2026 | Completed | Communication for Online Training | 1:03 | https://drive.google.com/file/d/1dyTpht9-P_1nsHXPBcUUb5Pe-L0i_EKF/view?usp=drive_link
[5 empty] | Dale's Cone of Experience | 27.07.2026 | 28.07.2026 | Parasuraman | Completed |  | 29.07.2026 | 30.07.2026 | Completed | Dale's Cone of Experience | 0:08 | https://drive.google.com/file/d/1_bNKqqXmZ_Bz9kJQSTDbPNQwetqqYZPb/view?usp=drive_link
[5 empty] | Roles of Audio - Visual Aids | 27.07.2026 | 27.07.2026 | Parasuraman | Completed |  | 28.07.2026 | 29.07.2026 | Completed | Roles of Audio - Visual Aids | 0:29 | https://drive.google.com/file/d/1HygrEw2DwfpP44WLLKCjghgY28S6bYds/view?usp=drive_link
[5 empty] | Transactional Analysis | 27.07.2026 | 27.07.2026 | Parasuraman | Completed |  | 28.07.2026 | 29.07.2026 | Completed | Transactional Analysis | 0:34 | https://drive.google.com/file/d/13WaWnbJ79z2Cs_PpLmnE4rhUG02yQ_0k/view?usp=drive_link
|  | EPIC-2026-PMeVidya 01 | Smt. Priya | Drone Technician | 50 Questions for Drone Technician | 14.07.2026 | 14.07.2026 | Antony / Parasuraman | Completed | LIVE SESSION | 15.07.2026 | 15.07.2026 | Completed | 50 Questions for Drone Technician | 1:09 | https://www.youtube.com/live/TaM7NYrEYYQ?si=t9AtzOz_82FGAjwE
|  | EPIC-2026-PMeVidya 02 | H.A. Manukumar | Advanced CNC Machinist | Cutting Speed & RPM Speed | 09.07.2026 | 09.07.2026 | Parasuraman | Completed | Bala | 10.07.2026 | 11.07.2026 | Completed | Cutting Speed & RPM Speed | 0:34 | https://drive.google.com/file/d/1Mgi-Ggq1CU_ZDKiAe8nSxCLjIrYz5ukh/view?usp=drive_link
[5 empty] | Face Milling Programming | 09.07.2026 | 10.07.2026 | Parasuraman | Completed | Bala | 13.07.2026 | 14.07.2026 | Completed | Face Milling Programming | 0:28 | https://drive.google.com/file/d/1GjQ1tOCse5ISo-vc9gPQY2O694PcOoiC/view?usp=drive_link
[5 empty] | Peck Drilling Cycle on VMC | 10.07.2026 | 10.07.2026 | Parasuraman | Completed | Bala | 13.07.2026 | 14.07.2026 | Completed | Peck Drilling Cycle on VMC | 0:26 | https://drive.google.com/file/d/1cYkY49iMICUlDMeZjBk4dVVd4fz2Pyyw/view?usp=drive_link
3 | August | EPIC-2026-PMeVidya 05 | Dr. Majji Bala Ganesh | AI Programming Assistant | 50 Questions for AI Programming Assistant | 30.08.2026 | 30.08.2026 | Parasuraman | Completed | LIVE SESSION | 31.08.2026 | 31.08.2026 | Completed | 50 Questions for AI Programming Assistant | 0:50 | https://www.youtube.com/live/NWOeFN322QY?si=CS5EgLMVsQJP_CXe
[5 empty] | AI (Artificial Intelligence Program Assistant) | 04.08.2026 | 04.08.2026 | Parasuraman | Completed | Ramaswamy | 05.08.2026 | 06.08.2026 | Completed | AI (Artificial Intelligence Program Assistant) | 0:35 | https://drive.google.com/file/d/1FmOQB4N_qzMFIb_MBpKFXTD6D-m4YgE_/view?usp=drive_link
[5 empty] | AI TOOLS (Artificial Intelligence) | 05.08.2026 | 05.08.2026 | Parasuraman | Completed | Ramaswamy | 06.08.2026 | 07.08.2026 | Completed | AI TOOLS (Artificial Intelligence) | 0:26 | https://drive.google.com/file/d/1Fzuy79rbY7gRYD1xezWyVo-1WwMaXzGS/view?usp=drive_link
[5 empty] | M2: Introduction of AI (Program Assistant - Computer Components) | 06.08.2026 | 06.08.2026 | Parasuraman | Completed | Ramaswamy | 07.08.2026 | 08.08.2026 | Completed | M2: Introduction of AI (Program Assistant - Computer Components) | 0:13 | https://drive.google.com/file/d/14UiWJmDCIFrAY1069xP9iPL2ewIBz_is/view?usp=drive_link
[5 empty] | M11: Machine Learning | 06.08.2026 | 07.08.2026 | Parasuraman | Completed | Ramaswamy | 10.08.2026 | 11.08.2026 | Completed | M11: Machine Learning | 0:30 | https://drive.google.com/file/d/10Tseq0I0DwYxcAjZC_E8rv6Ya_MXfbKs/view?usp=drive_link
[5 empty] | M13: Introduction of Computer Vision in AI | 07.08.2026 | 07.08.2026 | Parasuraman | Completed | Ramaswamy | 08.08.2026 | 10.08.2026 | Completed | M13: Introduction of Computer Vision in AI | 0:28 | https://drive.google.com/file/d/1vg7honuzlbZgCu8jTh0PcF1wsgg0rRDB/view?usp=drive_link
|  |  |  | Drone Technician | M1: Introduction of drone technician | 10.08.2026 | 10.08.2026 | Parasuraman | Completed | Bala | 11.08.2026 | 12.08.2026 | Completed | M1: Introduction of drone technician | 0:33 | https://drive.google.com/file/d/1Gg9b6yLR1cHEb8KSJgS0mMkelXMrJTIV/view?usp=drive_link
[5 empty] | M2: Introduction to 3d printer & their designs | 10.08.2026 | 11.08.2026 | Parasuraman | Completed | Bala | 12.08.2026 | 13.08.2026 | Completed | M2: Introduction to 3d printer & their designs | 0:23 | https://drive.google.com/file/d/1aux3YIMm26cfPfaeG0q5WYlfn2hvJvTx/view?usp=drive_link
[5 empty] | M6: Sensors used in drones | 11.08.2026 | 11.08.2026 | Parasuraman | Completed | Bala | 12.08.2026 | 13.08.2026 | Completed | M6: Sensors used in drones | 0:14 | https://drive.google.com/file/d/1VojNNyPbt4YxYI2tSIx4fmINFCCo2egf/view?usp=drive_link
[5 empty] | M7: BLDC Motors & Servo Motors in Drone | 12.08.2026 | 12.08.2026 | Parasuraman | Completed | Bala | 13.08.2026 | 14.08.2026 | Completed | M7: BLDC Motors & Servo Motors in Drone | 0:26 | https://drive.google.com/file/d/1cGhahnEvnosBHDRyfxQESaSIVx589kDe/view?usp=drive_link
[5 empty] | M9: FLIGHT CONTROLLER BOARD & ELECTRONIC SPEED CONTROLLER IN DRONE | 13.08.2026 | 13.08.2026 | Parasuraman | Completed | Bala | 14.08.2026 | 17.08.2026 | Completed | M9: FLIGHT CONTROLLER BOARD & ELECTRONIC SPEED CONTROLLER IN DRONE | 0:28 | https://drive.google.com/file/d/1mh2Cqf0kBjdqx1nE6EEHshfdvrl1L_qs/view?usp=drive_link
|  | EPIC-2026-PMeVidya 08 | Mrs. Rupasree | Instrument Mechanic | Scope and necessity of Instrumentation | 12.08.2026 | 12.08.2026 | Parasuraman | Completed | Ramaswamy | 13.08.2026 | 14.08.2026 | Completed | Scope and necessity of Instrumentation | 0:22 | https://drive.google.com/file/d/1EDl_AusljbgYfC_RaOIscpgWkVa4kvZ_/view?usp=drive_link
[5 empty] | Fundamentals of Electricity | 13.08.2026 | 13.08.2026 | Parasuraman | Completed | Ramaswamy | 14.08.2026 | 17.08.2026 | Completed | Fundamentals of Electricity | 0:19 | https://drive.google.com/file/d/1CocCtJZa8cwR0mQ6waUFnbcypRXtiCCY/view?usp=drive_link
[5 empty] | Semiconductors and Diodes | 14.08.2026 | 14.08.2026 | Parasuraman | Completed | Ramaswamy | 17.08.2026 | 18.08.2026 | Completed | Semiconductors and Diodes | 0:26 | https://drive.google.com/file/d/1188YLAHN83z2jgR35M6d77Th9-1NAMZp/view?usp=drive_link
[5 empty] | Rectifiers & Filters | 16.08.2026 | 16.08.2026 | Parasuraman | Completed | Ramaswamy | 17.08.2026 | 18.08.2026 | Completed | Rectifiers & Filters | 0:21 | https://drive.google.com/file/d/13JYjU3WBtqVscvSsriCMHcxd_nMpeMj3/view?usp=drive_link
[5 empty] | Pressure Measurement | 17.08.2026 | 17.08.2026 | Parasuraman | Completed | Ramaswamy | 18.08.2026 | 19.08.2026 | Completed | Pressure Measurement | 0:29 | https://drive.google.com/file/d/12O97NIkGI0F0to4IrcFx6wA0cloujuaI/view?usp=drive_link
[5 empty] | Pressure Measurement Introduction | 18.08.2026 | 18.08.2026 | Parasuraman | Completed | Ramaswamy | 19.08.2026 | 20.08.2026 | Completed | Pressure Measurement Introduction | 0:40 | https://drive.google.com/file/d/1mPJwb3CO5cFzcX98oLuKeH4m0DQqMuGM/view?usp=drive_link
[5 empty] | Flow Measurement | 19.08.2026 | 19.08.2026 | Parasuraman | Completed | Ramaswamy | 20.08.2026 | 21.08.2026 | Completed | Flow Measurement | 0:37 | https://drive.google.com/file/d/1Ml1W0GlliyM8ytroOsRz2BF7w34m-X97/view?usp=drive_link
[5 empty] | Level Measurement | 20.08.2026 | 20.08.2026 | Parasuraman | Completed | Ramaswamy | 21.08.2026 | 22.08.2026 | Completed | Level Measurement | 0:32 | https://drive.google.com/file/d/1lpXV_pAb3UeKme7Ri9jcY5zjklS85qN3/view?usp=drive_link
[5 empty] | Temperature Measurement | 21.08.2026 | 21.08.2026 | Parasuraman | Completed | Ramaswamy | 22.08.2026 | 24.08.2026 | Completed | Temperature Measurement | 0:22 | https://drive.google.com/file/d/10apqvSOC7R8OrD9dsHColCwutN-7Z2ZN/view?usp=drive_link
|  | EPIC-2026-PMeVidya 10 | CEO Apollo | Entreprenuership Development | PM Setu x Apollo MedSkills | 30.08.2026 |  | Antony Parasuraman | Completed | Parandhaman | 31.08.2026 |  | In Progress | PM Setu x Apollo MedSkills
|  | NA | Media SSC Stakeholder | Employability Skills | Unit 2: Self-Management Skills → Session 3: Self-confidence | NA | NA | NA | Received Digital content | NA | NA | NA | NA | Unit 2: Self-Management Skills → Session 3: Self-confidence | 0:38 | https://drive.google.com/file/d/13Ld5-n61TB7rVKl5qQm2y2r_4LdDgVeV/view?usp=sharing
|  |  |  | Employability Skills | Unit 2: Self-Management Skills → Session 3: Self-awareness | [8 empty] | Unit 2: Self-Management Skills → Session 3: Self-awareness | 0:21 | https://drive.google.com/file/d/10s9Uj1p02Ja7g0e8uYwVJEL_m__klH-H/view?usp=sharing
|  |  |  | Acting / Rasa Theory (Performing Arts) | Chapter 6: Rasa Adhyaya (Rasa Theory) | [8 empty] | Chapter 6: Rasa Adhyaya (Rasa Theory) | 0:15 | https://drive.google.com/file/d/1YNphn-JndRd8rnYPtM5Piw-yAjOuD7OL/view?usp=sharing
|  |  |  | Mass Media Studies | Unit 1: Understanding the Language of the Medium → Chapter II: Aspects of Film Language | [8 empty] | Unit 1: Understanding the Language of the Medium → Chapter II: Aspects of Film Language | 0:17 | https://drive.google.com/file/d/1qnOGc3EWO8y8Sw26U8o6G-KL_g4zP9zJ/view?usp=sharing
|  |  |  | Acting / Rasa Theory (Performing Arts) | Chapter 6: Rasa Adhyaya — Shanta Rasa | [8 empty] | Chapter 6: Rasa Adhyaya — Shanta Rasa | 0:21 | https://drive.google.com/file/d/1GmwayM3U66BxDOEnv1Kpq2ZMIJORwGGm/view?usp=sharing
4 | September | EPIC-2026-PMeVidya 11 | Dr. Majji Bala Ganesh | Drone Technician | M3: Identify & test various electronic, SMD components | 08.09.2026 | 08.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M3: Identify & test various electronic, SMD components | 0:48 | https://drive.google.com/file/d/1YtOeHJGH0FpqP7yHFWImmlCUrT1lm0N4/view?usp=drive_link
[5 empty] | M4: Measure different type electrical parameters and record the data relatd with Drone Hardware | 09.09.2026 | 09.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M4: Measure different type electrical parameters and record the data relatd with Drone Hardware | 0:34 | https://drive.google.com/file/d/1GIAAmPqPXwv3ka01aGarSiZVmACuGZyA/view?usp=drive_link
[5 empty] | M5: Identification of different type of batteries, battery specifications and their charging techniques used in drone | 10.09.2026 | 10.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M5: Identification of different type of batteries, battery specifications and their charging techniques used in drone | 0:40 | https://drive.google.com/file/d/1qSoY5c-CXu5ZGvTOrRmWIEJeLWxMfx8Z/view?usp=drive_link
[5 empty] | M8: Inspect, Test and Execute GPS Navigation and Telemetry Module, Different RF Blocks and Antennas Used In RF Transmitter and Receiver | 11.09.2026 | 11.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M8: Inspect, Test and Execute GPS Navigation and Telemetry Module, Different RF Blocks and Antennas Used In RF Transmitter and Receiver | 0:29 | https://drive.google.com/file/d/1ZHnGbAEmO2kqYhHxPk9Qgc8MpVV6cf10/view?usp=drive_link
[5 empty] | M10: Calibrate and troubleshoot Drone Gimbal and Drone Payload | 17.09.2026 | 17.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M10: Calibrate and troubleshoot Drone Gimbal and Drone Payload | 0:26 | https://drive.google.com/file/d/1bkWzPaZZ0VEYcwOU1m5bKkyX6H3VOSJx/view?usp=drive_link
[5 empty] | M11: Identify and resolved common error messages and corrections by Software debugging | 18.09.2026 | 18.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M11: Identify and resolved common error messages and corrections by Software debugging | 0:35 | https://drive.google.com/file/d/1BUhdFP57n62z6UJ5JNyMJat_FZLdH1U0/view?usp=drive_link
[5 empty] | M12: Inspect, Test and Execute Primary and Secondary Servicing with Troubleshoot Malfunctioning, and Repair Issues Discovered | 19.09.2026 | 19.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M12: Inspect, Test and Execute Primary and Secondary Servicing with Troubleshoot Malfunctioning, and Repair Issues Discovered | 0:59 | https://drive.google.com/file/d/1fMhwnw-yX3BfObZOIVyK2JTEjdaSX5hv/view?usp=drive_link
|  |  |  | AI Programming Assistant | M3: Using Operating System and Software Installation process - Part A | 25.09.2026 | 25.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M3: Using Operating System and Software Installation process - Part A | 1:10 | https://drive.google.com/file/d/1xDULSbQDcIkpD_0M_7NJZwOO7SXYTACY/view?usp=drive_link
[5 empty] | M3: Using Operating System and Software Installation process - Part B | 26.09.2026 | 26.09.2026 | Parasuraman | Completed | Ramaswamy |  |  | Completed | M3: Using Operating System and Software Installation process - Part B | 0:48 | https://drive.google.com/file/d/1_jiJSSrLe78dp-z1DCyvhBd8XzVs_lNi/view?usp=drive_link
|  | EPIC-2026-PMeVidya 15 | Shri M Mayapandi, ATO | Wireman | 1.9.50-55 - Earthing - Plate and pipe earthing | 28.09.2026 | 28.09.2026 | Parasuraman | Completed |  |  |  | In Progress | 1.9.50-55 - Earthing - Plate and pipe earthing
[5 empty] | 1.9.50-55 - Earthing - Rod, Strip and chemical earthing | 29.09.2026 | 29.09.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.9.50-55 - Earthing - Rod, Strip and chemical earthing
[5 empty] | 1.9.50-55 - Earthing - Comparision and measurement of earth resistance | 30.09.2026 | 30.09.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.9.50-55 - Earthing - Comparision and measurement of earth resistance
[5 empty] | 1.10.56 - 62 - DC Motor: Construction and Working | 01.10.2026 | 01.10.2026 | Parasuraman | Completed | Suganthan | 2026-03-10 | 2026-05-10 | COMPLETED | 1.10.56 - 62 - DC Motor: Construction and Working
[5 empty] | 1.10.56 - 62 - DC Motor: Types of Application | 05.10.2026 | 05.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.10.56 - 62 - DC Motor: Types of Application
[5 empty] | 1.10.56 - 62 - DC Motor: Speed Control and Characteristics | 06.10.2026 | 06.10.2026 | Parasuraman | Completed | Suganthan | 2026-05-10 | 2026-06-10 | COMPLETED | 1.10.56 - 62 - DC Motor: Speed Control and Characteristics | 0:36 | https://drive.google.com/file/d/1qMTJ5HTnW1Fyal3TWKsjMikmZt4cD5Nr/view?usp=drive_link
[5 empty] | 1.10.56-62 - DC Generator - Part 1 - Construction, Working & classification | 07.10.2026 | 07.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.10.56-62 - DC Generator - Part 1 - Construction, Working & classification
[5 empty] | 1.10.56-62 - DC Generator - Part 2 - EMF Equation | 08.10.2026 | 09.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.10.56-62 - DC Generator - Part 2 - EMF Equation
[5 empty] | 1.10.56-62 - DC Generator - Losses | 10.10.2026 | 10.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.10.56-62 - DC Generator - Losses
[5 empty] | 1.10.56-62 - DC Generator - Voltage Regulation | 14.10.2026 | 14.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.10.56-62 - DC Generator - Voltage Regulation
[5 empty] | 1.10.56-62 - DC Generator - Efficiency | 15.10.2026 | 15.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.10.56-62 - DC Generator - Efficiency
[5 empty] | 1.10.56-62 - DC Generator - Characteristics | 16.10.2026 | 16.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.10.56-62 - DC Generator - Characteristics
[5 empty] | 1.11.68 - AC Motor: Construction - Types, Control, working and starters | 21.10.2026 | 22.10.2026 | Parasuraman | Completed |  |  |  | COMPLETED | 1.11.68 - AC Motor: Construction - Types, Control, working and starters
[5 empty] | 1.6.32-36 - Measurement of AC circuit - Single Phase | 23.10.2026 | 23.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.6.32-36 - Measurement of AC circuit - Single Phase
|  | EPIC-2026-PMeVidya 12 | Shri A Gnanavel, ATO |  | 1.2.10 - 1.3.16 - Basic Workshop Practice (Hand Tools) | 26.09.2026 | 26.09.2026 | Parasuraman | Completed | Manikandan, Suganthan | 2006-07-10 | 2026-08-10 | COMPLETED | 1.2.10 - 1.3.16 - Basic Workshop Practice (Hand Tools) | 0:45 | https://drive.google.com/file/d/1UaBOvApH5sAix_QQA7znjGc8G0LhAVF2/view?usp=drive_link
[5 empty] | 1.11.63 - 1.11.68 - Transformer - Principle - Classification - EMF Equation | 28.09.2026 | 28.09.2026 | Parasuraman | Completed | Manikandan, Suganthan | 2026-09-10 | 2026-10-10 | COMPLETED | 1.11.63 - 1.11.68 - Transformer - Principle - Classification - EMF Equation | 0:43 | https://drive.google.com/file/d/14VMUQfaynRkucX_n95xPlZDNzgho4bIB/view?usp=drive_link
[5 empty] | 1.8.42 - 1.8.45 - Generation and Transmission - PowerPlant and overhead transmission | 29.09.2026 | 30.09.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.8.42 - 1.8.45 - Generation and Transmission - PowerPlant and overhead transmission
[5 empty] | 1.8.46 - 1.8.49 - Distribution & Substation - Circuit Breaker, Supply, CT, PT | 01.10.2026 | 05.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.8.46 - 1.8.49 - Distribution & Substation - Circuit Breaker, Supply, CT, PT
[5 empty] | 1.7.37 - 1.7.38 - Measuring Instruments - AM types, instruments scale, Classification | 07.10.2026 | 09.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.7.37 - 1.7.38 - Measuring Instruments - AM types, instruments scale, Classification
[5 empty] | 1.7.39 -41 - Measuring Instruments - Principles, MC, MI, Force types | 14.10.2026 | 16.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.7.39 -41 - Measuring Instruments - Principles, MC, MI, Force types
[5 empty] | 1.12.69 - 73 - Relay and Control Panel Wiring | 21.10.2026 | 23.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | 1.12.69 - 73 - Relay and Control Panel Wiring
5 | October | EPIC-2026-PMeVidya 16 | Shri Arun | Wireman | 1.4.21- 1.4.26 Basic Electrical Current . | 07.10.2026 | 08.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 2026-12-10 | 14-10-2026 | COMPLETED | 1.4.21- 1.4.26 Basic Electrical Current . | 0:47 | https://drive.google.com/file/d/1FpL5a4fZNfPFV52hw85TSwbR0h142_aA/view?usp=drive_link
[5 empty] | 1.5.27 - 1.5.30 Magnetism | 09.10.2026 | 10.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 13-10-2026 | 15-10-2026 | COMPLETED (3 PARTS) | 1.5.27 - 1.5.30 Magnetism - PART A | 0:09 | https://drive.google.com/file/d/1I9QuVIcPKD7T5BiSNzug_7AJGx9czw77/view?usp=drive_link
[5 empty] | 1.5.27 - 1.5.30 Magnetism | 09.10.2026 | 10.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 13-10-2026 | 15-10-2026 | COMPLETED | 1.5.27 - 1.5.30 Magnetism - PART B | 0:10 | https://drive.google.com/file/d/1cTsNXobGCCMEUzkM3M9yjvBCbRvXqnYr/view?usp=drive_link
[5 empty] | 1.5.27 - 1.5.30 Magnetism | 09.10.2026 | 10.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 13-10-2026 | 15-10-2026 | COMPLETED | 1.5.27 - 1.5.30 Magnetism - PART C | 0:20 | https://drive.google.com/file/d/1hxXMeQfYg9lAyzMu2XEIkFcxf1dqvn_J/view?usp=drive_link
[5 empty] | 1.5.27 - 1.5.30 Capacitor | 14.10.2026 | 15.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 16-10-2026 | 17-10-2026 | COMPLETED | 1.5.27 - 1.5.30 Capacitor | 0:23 | https://drive.google.com/file/d/1pzELn1Z4UfWUImgn_mEgJvTblTkdXw8h/view?usp=drive_link
|  | EPIC-2026-PMeVidya 17 | Shri Rakesh | Drone Pilot | 1.18.104 - 1.18.109 Cells and Batteries Part 1 | 15.10.2026 | 16.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 22-10-2026 | 22-10-2026 | COMPLETED | 1.18.104 - 1.18.109 Cells and Batteries Part 1 | 0:28 | https://drive.google.com/file/d/1tItEC0q1UNaF8YHQ-gihEhzS_-5pZw3p/view?usp=drive_link
[5 empty] | 1.18.104 - 1.18.109 Cells and Batteries Part 2 | 16.10.2026 | 17.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 22-10-2026 | 23-10-2026 | COMPLETED | 1.18.104 - 1.18.109 Cells and Batteries Part 2 | 0:38 | https://drive.google.com/file/d/1H73kffu3HxJF-TDdj_-dec2ZW5UV9XWn/view?usp=drive_link
[5 empty] | Introduction to RPA flying operation | 12.10.2026 | 13.10.2026 | Parasuraman | Completed | Manikandan, Suganthan | 23-10-2026 | 24-10-2026 | COMPLETED | Introduction to RPA flying operation
[5 empty] | Assembly of Drone | 13.10.2026 | 14.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | Assembly of Drone
[5 empty] | Weather conditions required for Drone | 15.10.2026 | 16.10.2026 | Parasuraman | Completed |  |  |  | Not Yet Started | Weather conditions required for Drone